## Procurement Log
Material | Supplier | Need By | Expected Delivery | Actual Delivery | Lead Time | Status
Lighting controls | Lutron | 2023-04-10 | 2023-04-10 | 2023-05-08 | 90 days | Delivered
Lighting controls | Lutron | 2023-09-05 | 2023-09-05 | 2023-09-29 | 12 weeks | Delivered
Custom millwork | Baker Millwork | 2023-05-15 | 2023-05-15 | 2023-06-26 | 10 weeks | Delivered
Custom millwork | Baker Millwork | 2023-10-02 | 2023-10-02 | 2023-10-30 | 10 weeks | Delivered
Switchgear | Eaton | 2023-03-01 | 2023-03-01 | 2023-03-20 | 84 | Delivered
Switchgear | Eaton | 2023-06-01 | 2023-06-01 | 2023-06-12 | 84 | Delivered
Storefront glazing | Oldcastle | 2023-07-01 | 2023-07-01 | 2023-07-01 | 8 weeks | Delivered
Door hardware | Allegion | 2023-04-01 | 2023-04-01 | 2023-04-01 | 21 | Delivered
Ceiling tile | Armstrong | 2023-05-01 | 2023-05-01 | 2023-04-28 | 14 | Delivered

## Schedule
Activity | Planned Start | Planned Finish | Actual Start | Actual Finish | Trade | % Complete
Hang drywall L1 | 2023-02-01 | 2023-02-20 | 2023-02-01 | 2023-02-24 | Drywall | 1
Hang drywall L2 | 2023-03-01 | 2023-03-22 | 2023-03-03 | 2023-03-30 | Drywall | 1
Paint L1 | 2023-03-05 | 2023-03-15 | 2023-03-06 | 2023-03-17 | Paint | 1
Paint L2 | 2023-03-23 | 2023-04-04 | 2023-04-03 | 2023-04-12 | Paint | 1
Install millwork | 2023-06-27 | 2023-07-24 | 2023-06-27 | 2023-08-04 | Millwork | 1
Install lighting controls | 2023-05-09 | 2023-05-30 | 2023-05-09 | 2023-06-02 | Electrical | 1
Ceiling grid | 2023-04-05 | 2023-04-14 | 2023-04-05 | 2023-04-14 | Ceilings | 1

## RFI Log
RFI # | Subject | Status | Due | Answer | Assigned To
1 | Switchgear clearance in electrical room | Closed | 2023-01-10 | Move 6 in. east per SK-4 | Architect
2 | Millwork finish at storefront | Closed | 2023-04-20 | Match sample 3 | Architect
3 | Lighting controls zone layout | Closed | 2023-03-28 | Revised layout issued | Engineer
4 | Ceiling height at fitting rooms | Closed | 2023-05-02 | Held at 9 ft | Architect

## Submittals
Submittal # | Title | Status | Review Due | Spec Section
101 | Lighting controls product data | Approved | 2023-02-14 | 26 09 23
102 | Millwork shop drawings | Approved | 2023-03-30 | 06 40 00
103 | Switchgear submittal | Revise and resubmit | 2023-01-20 | 26 24 13